## Architectural Analysis
Category | Measurement | Value
Building Analysis
Building Analysis | Total Internal Length | 150m
Building Analysis | Total Internal Width | 400m
Building Analysis | Total Internal Height | 2.4m
Building Analysis | Total External Length | 150.6m
Building Analysis | Total External Width | 400.6m
Building Analysis | Total External Height | 2.7m
Building Analysis | Total Internal Floor Area | 60000.0m²
Building Analysis | Total External Floor Area | 60330.4m²
Building Analysis | Total Internal Wall Area | 109.2m²
Building Analysis | Total External Wall Area | 128.5m²
Building Analysis | Total Volume | 306.0m³
Room Details
Room 1 | Name | Bathroom
Room 1 | Internal Length | 5.2m
Room 1 | Internal Width | 4.5m
Room 1 | Internal Height | 2.4m
Room 1 | External Length | 5.6m
Room 1 | External Width | 4.9m
Room 1 | External Height | 2.7m
Room 1 | Internal Floor Area | 23.4m²
Room 1 | External Floor Area | 27.4m²
Room 1 | Wall Surface Area | 46.8m²
Room 1 | Ceiling Area | 23.4m²
Room 1 | Skirting Board Length | 19.4m
Room 2 | Name | Kitchen
Room 2 | Internal Length | 4.2m
Room 2 | Internal Width | 3.5m
Room 2 | Internal Height | 2.4m
Room 2 | External Length | 4.6m
Room 2 | External Width | 3.9m
Room 2 | External Height | 2.7m
Room 2 | Internal Floor Area | 14.7m²
Room 2 | External Floor Area | 17.9m²
Room 2 | Wall Surface Area | 36.8m²
Room 2 | Ceiling Area | 14.7m²
Room 2 | Skirting Board Length | 15.4m
Room 3 | Name | Utility
Room 3 | Internal Length | 4.8m
Room 3 | Internal Width | 4.0m
Room 3 | Internal Height | 2.4m
Room 3 | External Length | 5.2m
Room 3 | External Width | 4.4m
Room 3 | External Height | 2.7m
Room 3 | Internal Floor Area | 19.2m²
Room 3 | External Floor Area | 22.9m²
Room 3 | Wall Surface Area | 42.2m²
Room 3 | Ceiling Area | 19.2m²
Room 3 | Skirting Board Length | 17.6m
Room 4 | Name | Living
Room 4 | Internal Length | 2.5m
Room 4 | Internal Width | 2.0m
Room 4 | Internal Height | 2.4m
Room 4 | External Length | 2.9m
Room 4 | External Width | 2.4m
Room 4 | External Height | 2.7m
Room 4 | Internal Floor Area | 5.0m²
Room 4 | External Floor Area | 7.0m²
Room 4 | Wall Surface Area | 21.6m²
Room 4 | Ceiling Area | 5.0m²
Room 4 | Skirting Board Length | 9.0m
Wall Details
Wall Details | External Wall Thickness | 0.3m
Wall Details | Internal Wall Thickness | 0.1m
Wall Details | Total Wall Length | 45.6m
Wall Details | External Wall Length | 28.2m
Wall Details | Internal Wall Length | 17.4m
Openings
Openings | Type 1 | Door
Openings | Width 1 | 0.9m
Openings | Height 1 | 2.1m
Openings | Quantity 1 | 6
Openings | Type 2 | Window
Openings | Width 2 | 1.2m
Openings | Height 2 | 1.0m
Openings | Quantity 2 | 8

## Materials Quantities
Category | Material | Quantity | Unit
Structural Materials
Structural Materials | Concrete Cubic Meters | 15 | m³
Structural Materials | Rebar Tons | 1.2 | tons
Structural Materials | Formwork Square Meters | 50 | m²
Walls
Walls | Bricks Units | 7000 | units
Walls | Blocks Units | 2500 | units
Walls | Mortar Kilograms | 2500 | kg
Walls | Paint Liters | 40 | L
Flooring
Flooring | Concrete Cubic Meters | 10 | m³
Flooring | Tile Square Meters | 60 | m²
Flooring | Carpet Square Meters | 40 | m²
Ceiling
Ceiling | Drywall Square Meters | 110 | m²
Ceiling | Paint Liters | 25 | L
Roofing
Roofing | Roof Tiles Square Meters | 120 | m²
Roofing | Roof Felt Square Meters | 110 | m²
Roofing | Roof Battens Meters | 200 | m
Doors And Windows
Doors And Windows | Doors Units | 8 | units
Doors And Windows | Windows Square Meters | 18 | m²
Finishes
Finishes | Paint Liters | 50 | L
Finishes | Tiles Square Meters | 20 | m²
Finishes | Skirting Board Meters | 40 | m
Electrical
Electrical | Cable Meters | 500 | m
Electrical | Sockets Units | 20 | units
Electrical | Switches Units | 12 | units
Plumbing
Plumbing | Pipe Meters | 200 | m
Plumbing | Fittings Units | 50 | units
Plumbing | Sanitary Fixtures Units | 5 | units
Hvac
Hvac | Ductwork Meters | 100 | m
Hvac | Units Units | 2 | units

## Construction Tasks
Phase | Task | Description | Duration (days) | Dependencies
Project Timeline | Start Date | 2025-04-21
Project Timeline | Estimated Completion Date | 2117-04-19
Project Timeline | Total Duration |  | 33600
Pre-Construction |  |  | 2100
Pre-Construction | Site Preparation | Clear the site, establish temporary facilities, and set up site security. | 1200
Pre-Construction | Excavation | Excavate the site to the required depth for foundations. | 900 | Site Preparation
Foundation |  |  | 3000
Foundation | Foundation Construction | Construct the concrete foundations according to the architectural plans. | 2400 | Excavation
Foundation | Damp Proofing | Apply damp proofing to the foundations to prevent moisture ingress. | 600 | Foundation Construction
Structural Frame |  |  | 3600
Structural Frame | Frame Construction | Construct the main structural frame of the building. | 3600 | Damp Proofing
Walls and Partitions |  |  | 4800
Walls and Partitions | External Wall Construction | Construct the external walls using bricks/blocks and mortar. | 3000 | Frame Construction
Walls and Partitions | Internal Partition Construction | Construct the internal walls and partitions. | 1800 | External Wall Construction
Roofing |  |  | 4200
Roofing | Roof Structure | Construct the roof structure including trusses and battens. | 2400 | External Wall Construction
Roofing | Roof Covering | Install the roof covering, including tiles/slates and felt. | 1800 | Roof Structure
Doors and Windows |  |  | 2100
Doors and Windows | Window Installation | Install all windows according to the architectural plans. | 1200 | External Wall Construction
Doors and Windows | Door Installation | Install all external and internal doors. | 900 | Internal Partition Construction
Services |  |  | 6000
Services | Electrical Installation | Install all electrical wiring, sockets, switches, and fixtures. | 2400 | Internal Partition Construction
Services | Plumbing Installation | Install all water supply and waste pipes, and sanitary fixtures. | 2100 | Internal Partition Construction
Services | HVAC Installation | Install heating, ventilation, and air conditioning systems. | 1800 | Electrical Installation, Plumbing Installation
Finishes |  |  | 6000
Finishes | Plastering | Apply plaster to all internal walls and ceilings. | 2100 | Electrical Installation, Plumbing Installation
Finishes | Flooring | Install all floor finishes including tiles, carpet, and timber. | 1800 | Plastering
Finishes | Painting and Decorating | Paint all internal walls, ceilings, and woodwork. | 2400 | Plastering
Final |  |  | 1800
Final | Snagging | Identify and fix any defects or issues. | 1200 | Painting and Decorating, Flooring
Final | Final Inspection | Conduct a final inspection of the completed building. | 1 | Snagging
Final | Handover | Hand over the completed building to the client. | 1 | Final Inspection